## Tham so thuat toan
Tham số thuật toán DLHS
Key | Value
HMS | 60
BW_max | 2
BW_min | 1
PSLSize | 5
numOfSub | 4
R | 100
Max_FEs | 20000

## Thong_Tin_Du_An
ID_KPI_Target | Target A
0.88
Start Time | End Time
12/4/2017, 12:00:00 AM | 11/1/2021, 12:00:00 AM

## Ket_qua_phan_bo
Thông tin phân bổ
Task ID (Task Name) | Start Time | End Time | AssigneeId (Assignee Name) | AssetId (Asset Name)
3 (Productize ER3 of RHOM) | 12/4/2017, 8:00:00 AM | 12/4/2017, 9:40:20 AM | 5 (Pavel Kralik) | [ ]
60 (Unable test io.enmasse.systemtest.brokered.clients.rhea.MsgPatternsTest.testMessageSelectorTopic) | 12/4/2017, 8:00:00 AM | 12/4/2017, 1:59:40 PM | 5 (Pavel Kralik) | [ ]
52 ([#991] : system-tests: new scale test: testCreditLimitation ({sharded,pooled}{queues,topics})) | 12/4/2017, 8:00:00 AM | 12/6/2017, 9:37:40 AM | 5 (Pavel Kralik) | [ ]
43 ([#811] : Brokered: cannot create topic: user null does not have permissions to 'send'...) | 12/4/2017, 8:00:00 AM | 12/6/2017, 3:41:00 PM | 6 (Rob Godfrey) | [ ]
53 ([#996] : system-tests: look at longtime running tests and fix them) | 12/4/2017, 8:00:00 AM | 12/6/2017, 3:51:00 PM | 1 (David Kornel) | [ ]
57 ([#998] : system-tests: review list of February disabled tests) | 12/4/2017, 8:00:00 AM | 12/7/2017, 8:15:19 AM | 4 (Ulf Lilleengen) | [ ]
45 ([#894] : Console does not sanitize address config names) | 12/4/2017, 8:00:00 AM | 12/11/2017, 8:20:20 AM | 5 (Pavel Kralik) | [ ]
40 ([#844] : system-tests: create documentation in HACKING doc how to execute webconsole tests) | 12/4/2017, 8:00:00 AM | 12/11/2017, 2:23:20 PM | 1 (David Kornel) | [ ]
46 ([#910] : address-controller can't replace addresses created via console) | 12/4/2017, 8:00:00 AM | 12/11/2017, 2:28:20 PM | 4 (Ulf Lilleengen) | [ ]
44 ([#877] : Make ansible deployment for install dependencies for running systemtests) | 12/4/2017, 8:00:00 AM | 12/11/2017, 3:20:00 PM | 1 (David Kornel) | [ ]
8 ([#749] : Use statefulsets for brokers) | 12/4/2017, 8:00:00 AM | 12/12/2017, 3:43:00 PM | 6 (Rob Godfrey) | [ ]
50 ([#921] : system-tests: new Plan test: testPlansAvailableViaConsole) | 12/4/2017, 8:00:00 AM | 12/15/2017, 2:14:00 PM | 7 (Jennifer Malloy) | [ ]
49 ([#920] : system-tests: new scale test: testCreditLimitation) | 12/4/2017, 8:00:00 AM | 12/15/2017, 3:02:00 PM | 3 (Gordon Sim) | [ ]
28 (Polarion reporting of enmasse test cases) | 12/4/2017, 8:00:00 AM | 12/18/2017, 8:11:40 AM | 7 (Jennifer Malloy) | [ ]
51 ([#936] : system-tests: create new test for thorough testing of REST API for address/address-space) | 12/4/2017, 8:00:00 AM | 12/18/2017, 8:30:40 AM | 8 (Tomas Kratky) | [ ]
9 ([#744] : Implement Plan resource limits for address space) | 12/4/2017, 8:00:00 AM | 12/18/2017, 9:02:00 AM | 5 (Pavel Kralik) | [ ]
12 ([#745] : Implement Plan resource requests for addresses) | 12/4/2017, 8:00:00 AM | 12/18/2017, 9:02:20 AM | 1 (David Kornel) | [ ]
64 ([#524] : System-tests: longtime: create new test for user authentication before/after restarting keycloak) | 12/4/2017, 8:00:00 AM | 12/18/2017, 2:06:39 PM | 8 (Tomas Kratky) | [ ]
63 ([#539] : System-tests: createtestAuthSendReceiveLong) | 12/4/2017, 8:00:00 AM | 12/18/2017, 2:08:59 PM | 5 (Pavel Kralik) | [ ]
48 ([#919] : system-tests: new scale test: testPodsLimitation) | 12/4/2017, 8:00:00 AM | 12/18/2017, 3:01:20 PM | 3 (Gordon Sim) | [ ]
34 ([#775] : Tests for clients authorization) | 12/4/2017, 8:00:00 AM | 12/18/2017, 3:12:59 PM | 6 (Rob Godfrey) | [ ]
30 ([#774] : Tests for authorization in WebConsole) | 12/4/2017, 8:00:00 AM | 12/18/2017, 3:13:20 PM | 3 (Gordon Sim) | [ ]
33 ([#776] : Recheck and enable system tests for standard address space) | 12/4/2017, 8:00:00 AM | 12/19/2017, 3:14:19 PM | 1 (David Kornel) | [ ]
39 ([#843] : improve test framework regarding to definition of dynamically created plans) | 12/4/2017, 8:00:00 AM | 12/19/2017, 3:21:40 PM | 3 (Gordon Sim) | [ ]
29 ([#773] : Tests for authentication WebConsole) | 12/4/2017, 8:00:00 AM | 12/20/2017, 8:07:00 AM | 8 (Tomas Kratky) | [ ]
61 ([#526] : System-tests: November list of disabled tests) | 12/4/2017, 8:00:00 AM | 12/20/2017, 3:07:40 PM | 7 (Jennifer Malloy) | [ ]
54 ([#907] : system-tests: add parametr for disable 'tear down' methods in systemtests) | 12/4/2017, 8:00:00 AM | 12/20/2017, 3:40:20 PM | 2 (Ernest Allen) | [ ]
56 (System-tests: periodical maintenance of systemtests and CI) | 12/4/2017, 8:00:00 AM | 12/28/2017, 9:21:40 AM | 4 (Ulf Lilleengen) | [ ]
47 ([#918] : system-tests: new scale test: testScaleRouterAutomatically) | 12/4/2017, 8:00:00 AM | 1/1/2018, 9:12:00 AM | 3 (Gordon Sim) | [ ]
36 ([#777] : Rewrite Jenkinsfile-long to declarative pipeline syntax) | 12/4/2017, 8:00:00 AM | 1/2/2018, 3:07:39 PM | 6 (Rob Godfrey) | [ ]
7 ([#747] : Add support for colocated topics) | 12/4/2017, 8:00:00 AM | 1/3/2018, 8:07:20 AM | 5 (Pavel Kralik) | [ ]
31 ([#770] : Define tests for limitation of address-spaces (by credits)) | 12/4/2017, 8:00:00 AM | 1/3/2018, 8:35:39 AM | 1 (David Kornel) | [ ]
21 ([#762] : How to match plans offered to plans specified (e.g. have console offer plans based on the presence of configmaps in its namespace or variations of that)) | 12/4/2017, 8:00:00 AM | 1/3/2018, 8:48:40 AM | 7 (Jennifer Malloy) | [ ]
42 (Investigate options for enforcing backlog limits on broker/router) | 12/4/2017, 8:00:00 AM | 1/3/2018, 2:47:40 PM | 5 (Pavel Kralik) | [ ]
15 ([#761] : Console to support status for addresses) | 12/4/2017, 8:00:00 AM | 1/4/2018, 10:14:00 AM | 2 (Ernest Allen) | [ ]
32 ([#772] : WebConsole Tests for addresses status) | 12/4/2017, 8:00:00 AM | 1/8/2018, 3:44:19 PM | 8 (Tomas Kratky) | [ ]
24 ([#768] : Disable MQTT (configurable upstream?)) | 12/4/2017, 8:00:00 AM | 1/9/2018, 9:17:00 AM | 6 (Rob Godfrey) | [ ]
13 ([#752] : Need to be able to configure address-controller to use wildcard cert for route certs) | 12/4/2017, 8:00:00 AM | 1/15/2018, 8:30:20 AM | 6 (Rob Godfrey) | [ ]
22 ([#755] : Productize: router, queue-scheduler, standard-controller, alter keycloak to be init-container image) | 12/4/2017, 8:00:00 AM | 1/15/2018, 9:15:40 AM | 8 (Tomas Kratky) | [ ]
25 ([#753] : Tie user identity creating address spaces and addresses to billing (i.e. reliable record of addresses spaces used against some identity for the customer)) | 12/4/2017, 8:00:00 AM | 1/15/2018, 9:16:00 AM | 2 (Ernest Allen) | [ ]
6 ([#746] : Add support for checking requests against limits and setting status on address) | 12/4/2017, 8:00:00 AM | 1/15/2018, 3:43:00 PM | 5 (Pavel Kralik) | [ ]
10 ([#748] : Persist decision about where queues/topics are placed) | 12/4/2017, 8:00:00 AM | 1/15/2018, 3:43:40 PM | 3 (Gordon Sim) | [ ]
55 ([#997] : system-tests: rewrite to junit5 2. step (reduce inheritance of TestBases)) | 12/4/2017, 8:00:00 AM | 1/15/2018, 3:51:00 PM | 6 (Rob Godfrey) | [ ]
62 ([#523] : SystemTests: brokered/standard: new test for keycloak persistent storage) | 12/4/2017, 8:00:00 AM | 1/23/2018, 2:18:00 PM | 2 (Ernest Allen) | [ ]
14 ([#767] : Disable durable subs (configurable upstream?)) | 12/4/2017, 8:00:00 AM | 1/29/2018, 8:13:20 AM | 1 (David Kornel) | [ ]
37 (Setup Jenkins job with productized images) | 12/4/2017, 8:00:00 AM | 1/31/2018, 3:14:40 PM | 8 (Tomas Kratky) | [ ]
27 ([#758] : Keycloak plugin OAUTH2 support) | 12/4/2017, 8:00:00 AM | 2/5/2018, 9:04:20 AM | 3 (Gordon Sim) | [ ]
17 ([#751] : Use valid wildcart cert) | 12/4/2017, 8:00:00 AM | 2/6/2018, 3:07:00 PM | 6 (Rob Godfrey) | [ ]
26 ([#757] : Oauth for console) | 12/4/2017, 8:00:00 AM | 2/12/2018, 3:08:00 PM | 6 (Rob Godfrey) | [ ]
68 ([#516] : System-tests: create testCreateDeleteAddressesViaAgentLong) | 12/4/2017, 8:00:00 AM | 3/5/2018, 3:51:40 PM | 1 (David Kornel) | [ ]
59 ([#548] : System-tests: framework(clients tests): add comments what value can be set for each parameter) | 12/4/2017, 8:00:00 AM | 3/16/2018, 8:54:00 AM | 7 (Jennifer Malloy) | [ ]
19 ([#765] : Changes to service broker (service type is just address space, different plans are supported. See also point above about how to tie plans offered to plans specified) ) | 12/4/2017, 8:00:00 AM | 3/22/2018, 10:39:20 AM | 7 (Jennifer Malloy) | [ ]
20 ([#759] : Delegate from keycloak to OpenShift Pro) | 12/4/2017, 8:00:00 AM | 3/22/2018, 10:39:40 AM | 4 (Ulf Lilleengen) | [ ]
65 ([#517] : System-tests: create testCreateDeleteAddressSpaceViaAgentLong) | 12/4/2017, 8:00:00 AM | 5/22/2018, 8:06:20 AM | 5 (Pavel Kralik) | [ ]
41 (Add Documentation Conventions to Guide) | 12/4/2017, 8:00:00 AM | 9/5/2018, 9:37:00 AM | 5 (Pavel Kralik) | [ ]
66 ([#547] : System-tests: multitenant: Support multiple address controllers in the same OpenShift cluster) | 12/4/2017, 8:00:00 AM | 10/16/2018, 9:04:40 AM | 8 (Tomas Kratky) | [ ]
67 ([#515] : System-tests: create testSendReceiveWithCreatingAlreadyCreatedAddressesLong) | 12/4/2017, 8:00:00 AM | 10/22/2018, 9:34:00 AM | 6 (Rob Godfrey) | [ ]
11 ([#750] : Handle scaledown of queues and topics at deploy time) | 12/4/2017, 8:00:00 AM | 12/13/2018, 3:49:20 PM | 4 (Ulf Lilleengen) | [ ]
18 ([#764] : Some level of metrics on address controller / standard controller to show prometheus metrics) | 12/4/2017, 8:00:00 AM | 12/13/2018, 3:49:20 PM | 6 (Rob Godfrey) | [ ]
35 ([#778] : Integrate PUMBA into our testing environment? (task already exists for that, from Ulf) ) | 12/4/2017, 8:00:00 AM | 4/30/2019, 9:08:39 AM | 7 (Jennifer Malloy) | [ ]
16 ([#756] : Monitoring for operator(us): prometheus for alerting and metrics, log aggregation/search for logs) | 12/4/2017, 8:00:00 AM | 4/30/2019, 9:53:40 AM | 7 (Jennifer Malloy) | [ ]
5 (Document Creating and deleting addresses) | 12/4/2017, 8:00:00 AM | 5/9/2019, 3:12:20 PM | 2 (Ernest Allen) | [ ]
2 ([#604] : Address-controller: PUT method is not implemented) | 12/4/2017, 8:00:00 AM | 1/13/2020, 3:03:00 PM | 1 (David Kornel) | [ ]
1 ([#590] : TopicTest with wildcards failed due to user doesn't have permission='CREATE_ADDRESS') | 12/4/2017, 8:00:00 AM | 1/20/2020, 8:46:20 AM | 8 (Tomas Kratky) | [ ]
38 (Console: Create an Address wizard tooltip placement awkward) | 12/4/2017, 8:00:00 AM | 3/16/2020, 9:08:40 AM | 6 (Rob Godfrey) | [ ]
23 ([#754] : Deploying keycloak in an HA configuration) | 12/4/2017, 8:00:00 AM | 3/23/2020, 3:51:40 PM | 5 (Pavel Kralik) | [ ]
4 (Creating and deleting addresses) | 12/4/2017, 8:00:00 AM | 4/27/2020, 12:24:20 PM | 4 (Ulf Lilleengen) | [ ]
58 (Console UI tweaks to Create Address wizard) | 12/4/2017, 8:00:00 AM | 5/27/2020, 8:19:39 AM | 3 (Gordon Sim) | [ ]
Các kết quả sau khi phân bổ
Target KPI Type A | Result KPI Type A | Start Time | End Time | Total Duration Works | Total Cost | Distance | Performence (s)
0.88 | 0.84661 | 12/4/2017, 8:00:00 AM | 5/27/2020, 8:19:39 AM | 905.0137 | 621655.3444 | nan | 66.1936
KPI Phân bổ
Employee ID Name | Employee ID | KPI Type A
David Kornel | 1 | 0.10548 | 0 | 0
Ernest Allen | 2 | 0.060786 | 0 | 0
Gordon Sim | 3 | 0.10204 | 0 | 0
Ulf Lilleengen | 4 | 0.072721 | 0 | 0
Pavel Kralik | 5 | 0.15285 | 0 | 0
Rob Godfrey | 6 | 0.15041 | 0 | 0
Jennifer Malloy | 7 | 0.099661 | 0 | 0
Tomas Kratky | 8 | 0.10267 | 0 | 0

## Lich_Nhan_Cong
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
1 | 53 | [#996] : system-tests: look at longtime running tests and fix them | 2017-12-04 01:00 | 2017-12-06 08:51 | Project Hien tai |  |  | 2.9813 | {} | null
1 | 40 | [#844] : system-tests: create documentation in HACKING doc how to execute webconsole tests | 2017-12-04 01:00 | 2017-12-11 07:23 | Project Hien tai |  |  | 6.7986 | {} | null
1 | 44 | [#877] : Make ansible deployment for install dependencies for running systemtests | 2017-12-04 01:00 | 2017-12-11 08:20 | Project Hien tai |  |  | 7.9167 | {} | null
1 | 12 | [#745] : Implement Plan resource requests for addresses | 2017-12-04 01:00 | 2017-12-18 02:02 | Project Hien tai |  |  | 14.1299 | {} | null
1 | 33 | [#776] : Recheck and enable system tests for standard address space | 2017-12-04 01:00 | 2017-12-19 08:14 | Project Hien tai |  |  | 15.9049 | {} | null
1 | 31 | [#770] : Define tests for limitation of address-spaces (by credits) | 2017-12-04 01:00 | 2018-01-03 01:36 | Project Hien tai |  |  | 30.0743 | {} | null
1 | 14 | [#767] : Disable durable subs (configurable upstream?) | 2017-12-04 01:00 | 2018-01-29 01:13 | Project Hien tai |  |  | 56.0278 | {} | null
1 | 68 | [#516] : System-tests: create testCreateDeleteAddressesViaAgentLong | 2017-12-04 01:00 | 2018-03-05 08:52 | Project Hien tai |  |  | 90.9826 | {} | null
1 | 2 | [#604] : Address-controller: PUT method is not implemented | 2017-12-04 01:00 | 2020-01-13 08:03 | Project Hien tai |  |  | 770.8812 | {} | null
1 | 1 | Phân tích quy trình nghiệp vụ khám bệnh | 2024-06-10 03:00 | 2024-06-17 10:00 | Project QK | Task 1 of data phan bo | 0.9 | 6.75 | {"year_of_exp":2,"english":2}
1 | 7 | Viết Code base Java-Angular | 2024-06-18 01:00 | 2024-06-24 07:00 | Project QK | Task 2 of data phan bo | 0.9 | 6.75 | {"year_of_exp":2,"backend":2,"frontend":1,"docker":1}
1 | 12 | Dựng trang homepage | 2024-06-24 07:00 | 2024-06-27 07:00 | Project QK | Task 3 of data phan bo | 0.95 | 3 | {"degree":2,"frontend":2,"year_of_exp":1}
1 | 52 | Đề xuất chiến lược kinh doanh gạch lát | 2024-06-27 07:00 | 2024-06-29 10:00 | Project QK | Task 13 of data phan bo | 0.95 | 2.375 | {"year_of_exp":2,"english":3}
1 | 41 | Lập kế hoạch cho dự án DCMA | 2024-06-30 01:00 | 2024-07-02 01:00 | Project QK | Task 10 of data phan bo | 0.9 | 2 | {"degree":2,"year_of_exp":3}
1 | 18 | Dựng giao diện module quản lý thầu | 2024-07-02 01:00 | 2024-07-08 05:00 | Project QK | Task 4 of data phan bo | 0.9 | 6.5 | {"year_of_exp":1,"backend":1,"frontend":2}
1 | 62 | Lập trình phía server module quản lý thầu | 2024-07-08 06:00 | 2024-07-14 10:00 | Project QK | Task 17 of data phan bo | 0.95 | 6.5 | {"year_of_exp":1,"backend":2,"frontend":2}
1 | 68 | Tách service quản lý thầu | 2024-07-15 01:00 | 2024-07-19 02:00 | Project QK | Task 18 of data phan bo | 0.85 | 4.25 | {"backend":2,"frontend":1,"manual_test":1}
1 | 32 | Kiểm thử luồng quản lý tài liệu | 2024-07-19 03:00 | 2024-07-21 10:00 | Project QK | Task 7 of data phan bo | 0.8 | 2.75 | {"manual_test":1,"unit_test":1,"automation_test":1}
1 | 48 | Điều chỉnh module quản lý thầu | 2024-07-21 01:00 | 2024-07-25 05:00 | Project QK | Task 12 of data phan bo | 0.95 | 4.5 | {"year_of_exp":2,"backend":2,"ci_cd":2,"frontend":1}
1 | 58 | Viết tài liệu công nghệ sử dụng | 2024-07-25 06:00 | 2024-07-26 10:00 | Project QK | Task 15 of data phan bo | 0.95 | 1.5 | {"year_of_exp":2,"backend":2,"frontend":2,"docker":2,"ci_cd":2}
1 | 1 | Phân tích nhu cầu học ngoại ngữ của sinh viên | 2024-07-27 08:00 | 2024-08-01 04:00 | Project outof |  |  | 4.5 | {"english":3,"year_of_exp":2} | []
1 | 3 | Phân tích yêu cầu sắp xếp lịch giảng dạy | 2024-09-30 08:00 | 2024-10-03 10:00 | Project outof |  |  | 3.25 | {"english":3,"year_of_exp":2} | []
1 | 4 | Lập kế hoạch cho dự án SSLG | 2024-10-04 01:00 | 2024-10-06 10:00 | Project outof |  |  | 3 | {"year_of_exp":2,"degree":2} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
2 | 54 | [#907] : system-tests: add parametr for disable 'tear down' methods in systemtests | 2017-12-04 01:00 | 2017-12-20 08:40 | Project Hien tai |  |  | 16.959 | {} | null
2 | 15 | [#761] : Console to support status for addresses | 2017-12-04 01:00 | 2018-01-04 03:14 | Project Hien tai |  |  | 31.2792 | {} | null
2 | 25 | [#753] : Tie user identity creating address spaces and addresses to billing (i.e. reliable record of addresses spaces used against some identity for the customer) | 2017-12-04 01:00 | 2018-01-15 02:16 | Project Hien tai |  |  | 42.1583 | {} | null
2 | 62 | [#523] : SystemTests: brokered/standard: new test for keycloak persistent storage | 2017-12-04 01:00 | 2018-01-23 07:18 | Project Hien tai |  |  | 50.7875 | {} | null
2 | 5 | Document Creating and deleting addresses | 2017-12-04 01:00 | 2019-05-09 08:12 | Project Hien tai |  |  | 521.9007 | {} | null
2 | 69 | Lập trình micro-service module quản lý sách | 2024-06-10 02:00 | 2024-06-13 05:00 | Project QK | Task 18 of data phan bo | fail | 3.375 | {"backend":1,"frontend":2,"manual_test":1}
2 | 2 | Phân tích quá trình nhập kho | 2024-06-13 06:00 | 2024-06-16 10:00 | Project QK | Task 1 of data phan bo | 0.96 | 3.5 | {"year_of_exp":1,"english":2}
2 | 53 | Đề xuất chiến lược mua hàng | 2024-06-17 01:00 | 2024-06-20 02:00 | Project QK | Task 13 of data phan bo | 0.95 | 3.125 | {"year_of_exp":2,"english":3}
2 | 39 | Viết kịch bản kiểm thử cho luồng nhập kho | 2024-06-18 05:00 | 2024-06-24 10:00 | Project QK | Task 9 of data phan bo | 0.9 | 6.5 | {"degree":2,"unit_test":2}
2 | 13 | Dựng trang landingpage | 2024-06-20 02:00 | 2024-06-23 05:00 | Project QK | Task 3 of data phan bo | 0.9 | 3.375 | {"degree":2,"frontend":2}
2 | 8 | Dựng code base Laravel-React | 2024-06-23 06:00 | 2024-06-29 10:00 | Project QK | Task 2 of data phan bo | 0.95 | 6.5 | {"year_of_exp":2,"backend":2,"frontend":1,"docker":1}
2 | 63 | Lập trình phía server module quản lý sách | 2024-07-01 03:00 | 2024-07-05 05:00 | Project QK | Task 17 of data phan bo | 0.95 | 4.25 | {"backend":2,"frontend":2}
2 | 19 | Dựng giao diện module quản lý nhân sự | 2024-07-05 06:00 | 2024-07-09 07:00 | Project QK | Task 4 of data phan bo | 0.9 | 4.125 | {"degree":1,"year_of_exp":1,"backend":1,"frontend":2}
2 | 23 | Triển khai module đấu thầu | 2024-07-09 07:00 | 2024-07-13 10:00 | Project QK | Task 5 of data phan bo | 0.9 | 4.375 | {"year_of_exp":1,"docker":2,"ci_cd":2}
2 | 36 | Sửa lỗi module quản lý phòng khách sạn | 2024-07-14 01:00 | 2024-07-19 05:00 | Project QK | Task 8 of data phan bo | 0.9 | 5.5 | {"year_of_exp":1,"backend":2,"frontend":1}
2 | 49 | Điều chỉnh module phân quyền | 2024-07-19 06:00 | 2024-07-24 06:00 | Project QK | Task 12 of data phan bo | 0.95 | 7 | {"year_of_exp":2,"backend":2,"ci_cd":2}
2 | 59 | Viết tài liệu hướng dẫn cài đặt | 2024-07-24 06:00 | 2024-07-26 10:00 | Project QK | Task 15 of data phan bo | 0.95 | 2.5 | {"year_of_exp":2,"backend":2,"frontend":2,"docker":2,"ci_cd":2}
2 | 5 | Dựng code base Java core | 2024-07-27 02:00 | 2024-08-01 10:00 | Project outof |  |  | 5.875 | {"year_of_exp":2,"backend":2,"frontend":2,"docker":1} | []
2 | 6 | Sửa lỗi chức năng Thêm vào giỏ | 2024-08-02 01:00 | 2024-08-03 08:00 | Project outof |  |  | 1.75 | {"year_of_exp":2,"backend":2,"frontend":1} | []
2 | 7 | Triển khai module quản lý thầu lên server | 2024-08-03 08:00 | 2024-08-08 10:00 | Project outof |  |  | 5.25 | {"year_of_exp":1,"docker":2,"ci_cd":2} | []
2 | 8 | Dựng trang giới thiệu sản phẩm | 2024-09-24 06:00 | 2024-09-24 10:00 | Project outof |  |  | 0.5 | {"degree":2,"frontend":2} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
3 | 49 | [#920] : system-tests: new scale test: testCreditLimitation | 2017-12-04 01:00 | 2017-12-15 08:02 | Project Hien tai |  |  | 11.8792 | {} | null
3 | 48 | [#919] : system-tests: new scale test: testPodsLimitation | 2017-12-04 01:00 | 2017-12-18 08:01 | Project Hien tai |  |  | 14.8778 | {} | null
3 | 30 | [#774] : Tests for authorization in WebConsole | 2017-12-04 01:00 | 2017-12-18 08:13 | Project Hien tai |  |  | 13.9028 | {} | null
3 | 39 | [#843] : improve test framework regarding to definition of dynamically created plans | 2017-12-04 01:00 | 2017-12-19 08:22 | Project Hien tai |  |  | 15.9201 | {} | null
3 | 47 | [#918] : system-tests: new scale test: testScaleRouterAutomatically | 2017-12-04 01:00 | 2018-01-01 02:12 | Project Hien tai |  |  | 26.15 | {} | null
3 | 10 | [#748] : Persist decision about where queues/topics are placed | 2017-12-04 01:00 | 2018-01-15 08:44 | Project Hien tai |  |  | 41.966 | {} | null
3 | 27 | [#758] : Keycloak plugin OAUTH2 support | 2017-12-04 01:00 | 2018-02-05 02:04 | Project Hien tai |  |  | 63.134 | {} | null
3 | 58 | Console UI tweaks to Create Address wizard | 2017-12-04 01:00 | 2020-05-27 01:20 | Project Hien tai |  |  | 905.041 | {} | null
3 | 3 | Phân tích tính khả thi dự án | 2024-06-13 01:00 | 2024-06-17 03:00 | Project QK | Task 1 of data phan bo | 0.85 | 4.25 | {"year_of_exp":2,"english":2}
3 | 55 | Đề xuất chiến lược nhập kho | 2024-06-18 01:00 | 2024-06-22 03:00 | Project QK | Task 13 of data phan bo | 0.9 | 4.25 | {"year_of_exp":2,"english":3}
3 | 9 | Dựng code base NodeJS-React | 2024-06-22 03:00 | 2024-06-29 05:00 | Project QK | Task 2 of data phan bo | 0.95 | 7.25 | {"backend":2,"frontend":1,"docker":1}
3 | 64 | Lập trình service phân quyền | 2024-06-29 07:00 | 2024-07-02 07:00 | Project QK | Task 17 of data phan bo | 0.9 | 3 | {"backend":2,"frontend":1}
3 | 29 | Kiểm thử chức năng nhập kho | 2024-07-02 07:00 | 2024-07-04 10:00 | Project QK | Task 7 of data phan bo | 0.9 | 2.375 | {"manual_test":1,"unit_test":2,"automation_test":1}
3 | 46 | Thu thập phản hồi của đối tác | 2024-07-05 01:00 | 2024-07-11 10:00 | Project QK | Task 11 of data phan bo | 0.9 | 7 | {"english":5,"degree":1}
3 | 50 | Điều chỉnh module quản lý nhân viên | 2024-07-12 01:00 | 2024-07-17 03:00 | Project QK | Task 12 of data phan bo | 0.85 | Task 12 of data phan bo | {"year_of_exp":2,"backend":2,"ci_cd":2}
3 | 24 | Triển khai module thanh toán | 2024-07-17 03:00 | 2024-07-22 05:00 | Project QK | Task 5 of data phan bo | 0.9 | 5.25 | {"year_of_exp":1,"docker":2,"ci_cd":2,"backend":1}
3 | 60 | Viết tài liệu triển khai | 2024-07-22 06:00 | 2024-07-24 10:00 | Project QK | Task 15 of data phan bo | 0.9 | 2.5 | {"year_of_exp":2,"backend":2,"frontend":2,"docker":2,"ci_cd":2}
3 | 9 | Dựng giao diện module mua hàng | 2024-07-27 01:00 | 2024-08-01 08:00 | Project outof |  |  | 5.75 | {"year_of_exp":1,"backend":1,"frontend":2} | []
3 | 10 | Lập trình infra | 2024-09-04 06:00 | 2024-09-08 06:00 | Project outof |  |  | 4 | {"year_of_exp":1,"docker":2,"ci_cd":2,"backend":1} | []
3 | 11 | Kiểm thử luồng mua hàng | 2024-09-08 06:00 | 2024-09-10 10:00 | Project outof |  |  | 2.5 | {"manual_test":1,"unit_test":2,"automation_test":1} | []
3 | 12 | Đề xuất ý tưởng cho giao diện mới | 2024-09-23 06:00 | 2024-09-24 10:00 | Project outof |  |  |  | {"year_of_exp":2,"english":3} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
4 | 57 | [#998] : system-tests: review list of February disabled tests | 2017-12-04 01:00 | 2017-12-07 01:15 | Project Hien tai |  |  | 3.0319 | {} | null
4 | 46 | [#910] : address-controller can't replace addresses created via console | 2017-12-04 01:00 | 2017-12-11 07:28 | Project Hien tai |  |  | 5.809 | {} | null
4 | 56 | System-tests: periodical maintenance of systemtests and CI | 2017-12-04 01:00 | 2017-12-28 02:22 | Project Hien tai |  |  | 24.1701 | {} | null
4 | 20 | [#759] : Delegate from keycloak to OpenShift Pro | 2017-12-04 01:00 | 2018-03-22 03:40 | Project Hien tai |  |  | 108.3326 | {} | null
4 | 11 | [#750] : Handle scaledown of queues and topics at deploy time | 2017-12-04 01:00 | 2018-12-13 08:49 | Project Hien tai |  |  | 374.9778 | {} | null
4 | 4 | Creating and deleting addresses | 2017-12-04 01:00 | 2020-04-27 05:24 | Project Hien tai |  |  | 873.5507 | {} | null
4 | 10 | Dựng code base NestJS-React | 2024-07-05 01:00 | 2024-07-11 10:00 | Project QK | Task 2 of data phan bo | 0.9 | 6.5 | {"backend":2,"frontend":1,"docker":1}
4 | 15 | Dựng trang chủ, thống kê phía admin | 2024-07-12 01:00 | 2024-07-18 05:00 | Project QK | Task 3 of data phan bo | 0.8 | 6.5 | {"degree":2,"frontend":2}
4 | 67 | Lập trình service module quản lý thẻ | 2024-07-18 06:00 | 2024-07-22 06:00 | Project QK | Task 17 of data phan bo | fail | 4 | {"backend":2,"frontend":2}
4 | 13 | Dựng các màn cho module đặt lịch | 2024-07-28 06:00 | 2024-08-03 10:00 | Project outof |  |  | 6.5 | {"degree":1,"frontend":2} | []
4 | 14 | Lập trình trang quản lý phân quyền | 2024-08-04 01:00 | 2024-08-08 10:00 | Project outof |  |  | 5 | {"degree":2,"frontend":1} | []
4 | 16 | Đọc hiểu code base | 2024-08-09 01:00 | 2024-08-11 10:00 | Project outof |  |  | 3 | {"backend":2,"frontend":1,"docker":1} | []
4 | 17 | Ghép API mô đun bán hàng | 2024-09-24 01:00 | 2024-10-02 10:00 | Project outof |  |  | 8 | {"frontend":1,"backend":1,"manual_test":1} | []
4 | 18 | Lập trình trang quảng bá, giới thiệu sản phẩm | 2024-10-04 01:00 | 2024-10-09 10:00 | Project outof |  |  | 6 | {"degree":2,"frontend":2} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
5 | 3 | Productize ER3 of RHOM | 2017-12-04 01:00 | 2017-12-04 02:40 | Project Hien tai |  |  | 0.20903 | {} | null
5 | 60 | Unable test io.enmasse.systemtest.brokered.clients.rhea.MsgPatternsTest.testMessageSelectorTopic | 2017-12-04 01:00 | 2017-12-04 07:00 | Project Hien tai |  |  | 0.74931 | {} | null
5 | 52 | [#991] : system-tests: new scale test: testCreditLimitation ({sharded,pooled}{queues,topics}) | 2017-12-04 01:00 | 2017-12-06 02:38 | Project Hien tai |  |  | 2.2035 | {} | null
5 | 45 | [#894] : Console does not sanitize address config names | 2017-12-04 01:00 | 2017-12-11 01:20 | Project Hien tai |  |  | 7.0424 | {} | null
5 | 9 | [#744] : Implement Plan resource limits for address space | 2017-12-04 01:00 | 2017-12-18 02:02 | Project Hien tai |  |  | 14.1292 | {} | null
5 | 63 | [#539] : System-tests: createtestAuthSendReceiveLong | 2017-12-04 01:00 | 2017-12-18 07:09 | Project Hien tai |  |  | 12.7687 | {} | null
5 | 7 | [#747] : Add support for colocated topics | 2017-12-04 01:00 | 2018-01-03 01:07 | Project Hien tai |  |  | 30.0153 | {} | null
5 | 42 | Investigate options for enforcing backlog limits on broker/router | 2017-12-04 01:00 | 2018-01-03 07:48 | Project Hien tai |  |  | 30.8493 | {} | null
5 | 6 | [#746] : Add support for checking requests against limits and setting status on address | 2017-12-04 01:00 | 2018-01-15 08:43 | Project Hien tai |  |  | 41.9646 | {} | null
5 | 65 | [#517] : System-tests: create testCreateDeleteAddressSpaceViaAgentLong | 2017-12-04 01:00 | 2018-05-22 01:06 | Project Hien tai |  |  | 169.0132 | {} | null
5 | 41 | Add Documentation Conventions to Guide | 2017-12-04 01:00 | 2018-09-05 02:37 | Project Hien tai |  |  | 275.2021 | {} | null
5 | 23 | [#754] : Deploying keycloak in an HA configuration | 2017-12-04 01:00 | 2020-03-23 08:52 | Project Hien tai |  |  | 839.9826 | {} | null
5 | 27 | Tạo kế hoạch kiểm thử đơn vị | 2024-02-07 03:00 | 2024-07-07 03:00 | Project QK | Task 6 of data phan bo | 0.95 | 5 | {"manual_test":2,"unit_test":1,"automation_test":1}
5 | 4 | Phân tích và tư vấn mua hàng cho KH | 2024-06-28 01:00 | 2024-07-02 03:00 | Project QK | Task 1 of data phan bo | 0.75 | 5.25 | {"year_of_exp":2,"english":2}
5 | 31 | Kiểm thử tính năng thêm vào giỏ | 2024-07-07 03:00 | 2024-07-09 05:00 | Project QK | Task 7 of data phan bo | 0.95 | 2.25 | {"manual_test":1,"unit_test":1,"automation_test":1}
5 | 37 | Viết kịch bản kiểm thử cho luồng thanh toán | 2024-07-09 06:00 | 2024-07-12 10:00 | Project QK | Task 9 of data phan bo | 0.95 | 3.5 | {"degree":2,"unit_test":2,"year_of_exp":1}
5 | 54 | Đề xuất chiến lược kinh doanh trực tuyến | 2024-07-13 01:00 | 2024-07-17 05:00 | Project QK | Task 13 of data phan bo | 0.8 | 4.5 | {"year_of_exp":2,"english":3}
5 | 56 | Lập tài liệu cuộc họp với khách hàng | 2024-07-17 06:00 | 2024-07-20 06:00 | Project QK | Task 14 of data phan bo | 0.8 | 3 | {"year_of_exp":2,"english":5}
5 | 19 | Viết kịch bản kiểm thử tích hợp | 2024-08-17 01:00 | 2024-08-21 10:00 | Project outof |  |  | 5 | {"manual_test":1,"unit_test":1,"automation_test":1} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
6 | 43 | [#811] : Brokered: cannot create topic: user null does not have permissions to 'send'... | 2017-12-04 01:00 | 2017-12-06 08:41 | Project Hien tai |  |  | 2.9604 | {} | null
6 | 8 | [#749] : Use statefulsets for brokers | 2017-12-04 01:00 | 2017-12-12 08:43 | Project Hien tai |  |  | 8.9646 | {} | null
6 | 34 | [#775] : Tests for clients authorization | 2017-12-04 01:00 | 2017-12-18 08:13 | Project Hien tai |  |  | 13.9021 | {} | null
6 | 36 | [#777] : Rewrite Jenkinsfile-long to declarative pipeline syntax | 2017-12-04 01:00 | 2018-01-02 08:08 | Project Hien tai |  |  | 29.891 | {} | null
6 | 24 | [#768] : Disable MQTT (configurable upstream?) | 2017-12-04 01:00 | 2018-01-09 02:17 | Project Hien tai |  |  | 36.1604 | {} | null
6 | 13 | [#752] : Need to be able to configure address-controller to use wildcard cert for route certs | 2017-12-04 01:00 | 2018-01-15 01:30 | Project Hien tai |  |  | 42.0632 | {} | null
6 | 55 | [#997] : system-tests: rewrite to junit5 2. step (reduce inheritance of TestBases) | 2017-12-04 01:00 | 2018-01-15 08:51 | Project Hien tai |  |  | 42.9813 | {} | null
6 | 17 | [#751] : Use valid wildcart cert | 2017-12-04 01:00 | 2018-02-06 08:07 | Project Hien tai |  |  | 64.8896 | {} | null
6 | 26 | [#757] : Oauth for console | 2017-12-04 01:00 | 2018-02-12 08:08 | Project Hien tai |  |  | 70.8917 | {} | null
6 | 67 | [#515] : System-tests: create testSendReceiveWithCreatingAlreadyCreatedAddressesLong | 2017-12-04 01:00 | 2018-10-22 02:34 | Project Hien tai |  |  | 322.1958 | {} | null
6 | 18 | [#764] : Some level of metrics on address controller / standard controller to show prometheus metrics | 2017-12-04 01:00 | 2018-12-13 08:49 | Project Hien tai |  |  | 374.9778 | {} | null
6 | 38 | Console: Create an Address wizard tooltip placement awkward | 2017-12-04 01:00 | 2020-03-16 02:09 | Project Hien tai |  |  | 832.1431 | {} | null
6 | 6 | Phân tích nhu cầu học tiếng Anh | 2024-06-09 01:00 | 2024-06-12 10:00 | Project QK | Task 1 of data phan bo | 0.95 | Task 1 of data phan bo | {"year_of_exp":2,"english":2}
6 | 42 | Lập kế hoạch cho dự án | 2024-06-20 01:00 | 2024-06-24 05:00 | Project QK | Task 10 of data phan bo | 0.85 | 4.5 | {"degree":2,"year_of_exp":3}
6 | 57 | Lập tài liệu cuộc họp với đối tác | 2024-06-24 06:00 | 2024-06-27 05:00 | Project QK | Task 14 of data phan bo | 0.9 | 3 | {"year_of_exp":2,"english":5}
6 | 28 | Tạo kế hoạch kiểm thử tích hợp | 2024-06-27 06:00 | 2024-07-01 10:00 | Project QK | Task 6 of data phan bo | 0.9 | 4.5 | {"manual_test":2,"unit_test":1}
6 | 38 | Viết kịch bản kiểm thử cho luồng đặt hàng | 2024-07-02 01:00 | 2024-07-04 01:00 | Project QK | Task 9 of data phan bo | 0.95 | 2 | {"degree":2,"unit_test":2}
6 | 33 | Kiểm thử tính năng Thêm chứng chỉ | 2024-07-04 01:00 | 2024-07-05 05:00 | Project QK | Task 7 of data phan bo | 0.8 | 1.5 | {"manual_test":1,"unit_test":1,"automation_test":1}
6 | 47 | Thu thập phản hồi của người dùng | 2024-07-05 06:00 | 2024-07-11 10:00 | Project QK | Task 11 of data phan bo | 0.95 | 6.5 | {"english":5}
6 | 24 | Xây dựng kịch bản thử nghiệm cho luồng quản lý hóa đơn | 2024-08-20 01:00 | 2024-08-24 10:00 | Project outof |  |  | 5 | {"degree":2,"unit_test":2} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
7 | 50 | [#921] : system-tests: new Plan test: testPlansAvailableViaConsole | 2017-12-04 01:00 | 2017-12-15 07:14 | Project Hien tai |  |  | 11.7792 | {} | null
7 | 28 | Polarion reporting of enmasse test cases | 2017-12-04 01:00 | 2017-12-18 01:12 | Project Hien tai |  |  | 14.0243 | {} | null
7 | 61 | [#526] : System-tests: November list of disabled tests | 2017-12-04 01:00 | 2017-12-20 08:08 | Project Hien tai |  |  | 16.891 | {} | null
7 | 21 | [#762] : How to match plans offered to plans specified (e.g. have console offer plans based on the presence of configmaps in its namespace or variations of that) | 2017-12-04 01:00 | 2018-01-03 01:49 | Project Hien tai |  |  | 30.1014 | {} | null
7 | 59 | [#548] : System-tests: framework(clients tests): add comments what value can be set for each parameter | 2017-12-04 01:00 | 2018-03-16 01:54 | Project Hien tai |  |  | 102.1125 | {} | null
7 | 19 | [#765] : Changes to service broker (service type is just address space, different plans are supported. See also point above about how to tie plans offered to plans specified) | 2017-12-04 01:00 | 2018-03-22 03:39 | Project Hien tai |  |  | 108.3319 | {} | null
7 | 35 | [#778] : Integrate PUMBA into our testing environment? (task already exists for that, from Ulf) | 2017-12-04 01:00 | 2019-04-30 02:09 | Project Hien tai |  |  | 512.1431 | {} | null
7 | 16 | [#756] : Monitoring for operator(us): prometheus for alerting and metrics, log aggregation/search for logs | 2017-12-04 01:00 | 2019-04-30 02:54 | Project Hien tai |  |  | 512.2368 | {} | null
7 | 5 | Phân tích quy trình nhập kho | 2024-06-09 01:00 | 2024-06-12 10:00 | Project QK | Task 1 of data phan bo | fail | 4 | {"year_of_exp":2,"english":2}
7 | 14 | Dựng trang chủ phía khách | 2024-06-13 01:00 | 2024-06-15 05:00 | Project QK | Task 3 of data phan bo | fail | 2.5 | {"degree":2,"frontend":2}
7 | 20 | Dựng giao diện module quản lý phòng ban | 2024-06-15 06:00 | 2024-06-21 10:00 | Project QK | Task 4 of data phan bo | 0.85 | 6.5 | {"degree":1,"year_of_exp":1,"backend":1,"frontend":2}
7 | 30 | Kiểm thử tính năng đồng bộ dữ liệu | 2024-06-22 01:00 | 2024-06-25 10:00 | Project QK | Task 7 of data phan bo | 0.9 | 4 | {"manual_test":1,"unit_test":2,"automation_test":1}
7 | 35 | Sửa lỗi module quản lý lịch đặt khách sạn | 2024-06-27 01:00 | 2024-07-02 03:00 | Project QK | Task 8 of data phan bo | 0.9 | 5.5 | {"year_of_exp":1,"backend":2,"frontend":1}
7 | 70 | Lập trình micro-service module phân quyền | 2024-07-02 03:00 | 2024-07-09 05:00 | Project QK | Task 18 of data phan bo | fail | 7.25 | {"backend":1,"frontend":2,"manual_test":1}
7 | 22 | Triển khai ứng dụng ở heroku | 2024-07-09 06:00 | 2024-07-15 05:00 | Project QK | Task 5 of data phan bo | 0.8 | 6 | {"year_of_exp":1,"docker":2,"ci_cd":2}
7 | 28 | Sửa lỗi module quản lý thuế TNCN | 2024-08-09 05:00 | 2024-08-11 05:00 | Project outof |  |  | 3 | {"year_of_exp":1,"backend":2,"frontend":1} | []
7 | 30 | Triển khai ứng dụng trên github | 2024-09-23 06:00 | 2024-09-24 10:00 | Project outof |  |  | 1.5 | {"year_of_exp":1,"docker":2,"ci_cd":2} | []
Emp ID | Task ID | Task name | StartTime | End Time | Task ở đâu | Task liên quan | point | estimate Time
8 | 51 | [#936] : system-tests: create new test for thorough testing of REST API for address/address-space | 2017-12-04 01:00 | 2017-12-18 01:31 | Project Hien tai |  |  | 14.0639 | {} | null
8 | 64 | [#524] : System-tests: longtime: create new test for user authentication before/after restarting keycloak | 2017-12-04 01:00 | 2017-12-18 07:07 | Project Hien tai |  |  | 14.7639 | {} | null
8 | 29 | [#773] : Tests for authentication WebConsole | 2017-12-04 01:00 | 2017-12-20 01:07 | Project Hien tai |  |  | 16.0146 | {} | null
8 | 32 | [#772] : WebConsole Tests for addresses status | 2017-12-04 01:00 | 2018-01-08 08:44 | Project Hien tai |  |  | 34.9674 | {} | null
8 | 22 | [#755] : Productize: router, queue-scheduler, standard-controller, alter keycloak to be init-container image | 2017-12-04 01:00 | 2018-01-15 02:16 | Project Hien tai |  |  | 42.1576 | {} | null
8 | 37 | Setup Jenkins job with productized images | 2017-12-04 01:00 | 2018-01-31 08:15 | Project Hien tai |  |  | 58.9056 | {} | null
8 | 66 | [#547] : System-tests: multitenant: Support multiple address controllers in the same OpenShift cluster | 2017-12-04 01:00 | 2018-10-16 02:05 | Project Hien tai |  |  | 316.1347 | {} | null
8 | 1 | [#590] : TopicTest with wildcards failed due to user doesn't have permission='CREATE_ADDRESS' | 2017-12-04 01:00 | 2020-01-20 01:46 | Project Hien tai |  |  | 775.0965 | {} | null
8 | 34 | Kiểm thử tính năng Sửa chứng chỉ | 2024-06-25 01:00 | 2024-06-29 10:00 | Project QK | Task 7 of data phan bo | 0.75 | 5 | {"manual_test":1,"unit_test":1,"automation_test":1}
8 | 40 | Viết kịch bản kiểm thử cho luồng xuất kho | 2024-06-30 01:00 | 2024-07-03 05:00 | Project QK | Task 9 of data phan bo | 0.8 | 3.5 | {"degree":2,"unit_test":2}
8 | 66 | Lập trình service gán nguồn lực | 2024-06-30 01:00 | 2024-07-03 05:00 | Project QK | Task 17 of data phan bo | 0.85 | 3.5 | {"backend":2,"frontend":2}
8 | 21 | Dựng giao diện thống kê nhân sự | 2024-07-03 06:00 | 2024-07-06 08:00 | Project QK | Task 4 of data phan bo | 0.8 | 3.25 | {"year_of_exp":1,"backend":1,"frontend":2}
8 | 71 | Lập trình service kết nối database | 2024-07-06 08:00 | 2024-07-12 08:00 | Project QK | Task 18 of data phan bo | 0.85 | 6 | {"backend":1,"frontend":2,"manual_test":1}
8 | 31 | Dựng các màn hình của chatbot | 2024-07-29 04:00 | 2024-08-02 10:00 | Project outof |  |  | 4.5 | {"degree":2,"frontend":2} | []
8 | 32 | Lập trình service chat với socket | 2024-08-09 01:00 | 2024-08-11 10:00 | Project outof |  |  | 4 | {"backend":2,"frontend":2} | []
8 | 33 | Dựng các màn hình trò chuyện | 2024-08-24 01:00 | 2024-08-29 10:00 | Project outof |  |  | 6 | {"degree":2,"frontend":3} | []
8 | 34 | Kiểm thử tính năng tạo cuộc họp | 2024-08-30 01:00 | 2024-09-01 10:00 | Project outof |  |  | 2 | {"manual_test":1,"unit_test":1,"automation_test":1} | []
8 | 35 | Dựng các màn hình của mô đun quản lý lớp học | 2024-09-17 02:00 | 2024-09-22 08:00 | Project outof |  |  | 5.625 | {"degree":2,"frontend":2} | []

## Lich_May_Moc
AssetID | Start Date | End Date | Thực hiện công việc trong dự án
2 | 7/1/2024, 3:00:00 PM | 7/20/2024, 3:00:00 PM | Công việc khác ngoài dự án
2 | 7/21/2024, 9:00:00 AM | 8/1/2024, 3:00:00 PM | Công việc khác ngoài dự án
2 | 8/1/2024, 9:00:00 AM | 8/10/2024, 3:00:00 PM | Công việc khác ngoài dự án
3 | 7/1/2024, 8:00:00 AM | 7/13/2024, 9:00:00 AM | Công việc khác ngoài dự án
3 | 7/13/2024, 9:00:00 AM | 7/25/2024, 3:00:00 PM | Công việc khác ngoài dự án
3 | 7/26/2024, 9:00:00 AM | 8/8/2024, 3:00:00 PM | Công việc khác ngoài dự án
4 | 7/1/2024, 3:00:00 PM | 7/15/2024, 3:00:00 PM | Công việc khác ngoài dự án
4 | 7/16/2024, 8:00:00 AM | 8/18/2024, 3:00:00 PM | Công việc khác ngoài dự án
4 | 8/19/2024, 8:00:00 AM | 9/24/2024, 3:00:00 PM | Công việc khác ngoài dự án
9 | 7/1/2024, 1:00:00 PM | 8/12/2024, 12:00:00 PM | Công việc khác ngoài dự án
9 | 8/12/2024, 12:00:00 PM | 9/8/2024, 12:00:00 PM | Công việc khác ngoài dự án